## Sheet1
Capstone Project Deliverable | Semester | Summer 2017
| Month | 5 |  |  |  |  | 6 |  |  |  | 7 |  |  |  |  | 8
| Day | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28
Project Team Identified
Project Brainstorming | [14 empty] | Complete
Dataset Top Choices Selected | [14 empty] | Not Complete |  |  |  |  | Project Plan
Proposal Documented
Final Dataset Chosen
Topic Context / Ethics Research
Topic Context / Ethics Documentation
Data Load and EDA
Dataset Dimensionality Reduction Padding
Dataset Clustering Padding
Dataset Model Predictions
Project Findings Documentation
Online Café Talk 1
First Paper Draft
Online Café Talk 2
BiWeekly Adviser Meeting
Second Paper Draft